## Sheet1
2013 Bond Needs
New Construction | Year Needed | Cost Estimate
Comprehensive High School #4 | 2015-2016 | 145501296
Middle School #8 | 2017-2018 | 48154067
Middle School #9 | 2023-2024 | 62531691
Elementary School #23 | 2015-2016 | 23714874
Elementary School #24 | 2019-2020 | 27027043
Elementary School #25 | 2020-2021 | 28302372
Elementary School #26 | 2021-2022 | 29639186
Elementary School #27 | 2023-2024 | 32509444
Guyer High School addition / 9th grade center | 2018-2019 | 48995431
Land Acquisitions |  | 30000000
New Construction / Land Sub-Total |  | 476375404
Elementary School Renovations
Borman Elementary
| Provide Covered Walkway from Exterior Door at Library to Drive | 50000
Evers Elementary
| Replace Standing Seam Roof / use energy efficient materials | 549871.875
Ginnings Elementary
| New roof in all old areas | 1400000
| Additional staff parking | 105000
Hodge Elementary
| Replace Standing Seam Roof / use energy efficient materials | 549871.875
McNair Elementary
| Replace Standing Seam Roof / use energy efficient materials | 549871.875
Newton Rayzor Elementary
| New Roof | 911629.6875
| Perimeter fence around playground | 20000
| Need workroom / storage space for all wings | Need A/E Input
| Literacy library to small, not enough educational materials in library as well | Need A/E Input
Rivera Elementary
| New Roof | 1093955.625
W.S. Ryan Elementary
| Flooring & carpet replacement throughout the building | 350000
| Painting / wainscoat / tackwall | 150000
Wilson Elementary
| New Roof | 911629.6875
| New millwork E, D, C and B halls. Refacing in office, and additional cabinetry in Nurses office | Need A/E Input
| We need D and C hall rooms to be handicapped accessible with solid doors with peek window for safety reasons | Need A/E Input
Middle School Renovations
Calhoun Middle School
| New Roof | 1504912.5
| Provide fence around perimeter of campus to control access to the site. Decorative fence - brick columns with wrought iron? | 150000
| Investigate existing restroom and improvements to partitions and fixtures. | Need A/E Input
| Repair and/or replace auditorium seating. | Need A/E Input
Crownover Middle School
| Covered walkway/canopy outside cafeteria. | 100000
McMath Middle School
| Covered walkway/canopy outside cafeteria. | 100000
Strickland Middle School
| New roof in all old areas | 416745
High School Renovations
Davis High School
| Need a science lab | Need A/E Input
| Need an additional elementary classroom | Need A/E Input
Denton High School
| New Bleachers & Press box at Baseball Field. | 195750
| Renovate Existing Baseball Field Restrooms. | Need A/E Input
| Replace Heating boilers in the main bldg | 142000
| Flooring Replacement - remove carpet in classrooms and replace with v.c.t. in some hallways/replace rubber stairs and ramps. (Investigate polished concrete) | Need A/E Input
| Repair and/or replace Lockers - Infill lockers in the foreign language wing. | Need A/E Input
| Investigate a new tile wainscot in main building - replace green tile. | Need A/E Input
| New Bleachers for tennis courts | 29000
Fred Moore High School
| Need Secured entry vestibule | 50000
| Fire Alarm System | 90000
| PA / Bell System | 90000
| Flooring & carpet replacement throughout the building including the gym | 100000
Ryan High School
| Replace Chillers in main bldg | 700000
| Press box at Baseball Field | 50000
Auxiliary Facility Renovations
ATC
| A covered walkway is needed for students who travel along bus lane. | Need A/E Input
| The carpeting in the lecture hall needs replacing due to severe stains and wear. | Need A/E Input
| The following is a list of spaces needed: Engineering lab with storage (newly added course) - Forensic science lab seems to allow about 10 students to work in there, when there are 25 in the class - Cosmetology needs more work space, due to losing 4 stations because of design - The culinary Kitchen cannot house the entire class - HSTE needs two more classrooms due to the amount of students. - Need a Pre-Vet lab (new course) - Majorly need storage by lecture hall. Tables are just put in the hallway. - Need an Air Craft Lab and Classroom (new course) - Need 2 more Advanced Credit Classrooms due to overflow. | Need A/E Input
| The bistro bar area needs some redesigning due to lack of space and obsolete equipment. There needs to be room for the warming oven, per Health Department. | Need A/E Input
Ann Windle School FYC
| New Roof | 367500
| Additional Parking. | Need A/E Input
| Replace all classroom, activity center & corridor carpet with rubber or marmoleum flooring. Office, library & Parent Training areas need new carpet. | Need A/E Input
| Expand current parent training room, library and classrooms (new pod). | Need A/E Input
| Provide a larger screen in activity center and a pull down screen in conference room. | Need A/E Input
| Work with SPED department on motor lab at activity center. Ensure current swing does not conflict with light fixtures. | Need A/E Input
Renovations Sub-Total |  | 10727738.125
Technology Items
Technology Information Officer to provide scope & pricing
Technology Sub-Total |  | 0
Energy Conservation Measures
Intelligent Irrigation |  | 1211000
Exterior Lighting Retrofit |  | 340000
Guyer High School - HVAC Retrofit |  | 32000
Energy Conservation Sub-Total |  | 1583000
| Total | 488686142.125